## Slide 1: MD 97 – Brookeville Bypass Construction Management at Risk (CMAR) Project
Presented By:
Sean Campion P.E.
Assistant Division Chief,
Innovative Contracting Division

## Slide 2: Overview
MD 97 – Brookeville Bypass Overview
Construction Management at Risk Project Delivery Overview
Overview of the Procurement Process

## Slide 3: Project Study Area

## Slide 4: Background
MD 97 is an arterial highway serving the east Montgomery County corridor and central Maryland from Washington, D.C. and the Capital Beltway (I-495) to I-70 in Howard County.
MD 97 functions as a major north-south commuter route between the employment areas in and surrounding Washington, D.C., and the residential communities north of Brookeville, including northern Montgomery County, Howard, and Frederick Counties.

## Slide 5: Need for improvement
Roadway deficiencies
“dog-leg” or “S” curve located along MD 97 (High Street, Market Street, and Georgia Avenue)
Increasing traffic volumes
ADT: 2013(10,400) 2033(12,700)
Truck: 5%
Need to preserve the historical character of the town
Brookeville is recognized as a historic district and was listed on the National Register of Historic Places in 1979.

## Slide 6: MD 97 Brookeville Bypass
  Purpose and Need –
  To remove the continually increasing traffic volumes from the Town of Brookeville, improve traffic operations and safety conditions on existing MD 97, and preserve the historic character of the town.
  Project Objectives –
    Construct a two-lane roadway to move the traffic from the town.
    Minimize environmental impacts (stream, wetland, forest, parkland, archeological features etc.).
    Preserve the historic character of the town.

## Slide 7: Selected Alternative

## Slide 8: Typical Section

## Slide 9: Project Elements:
Construction is anticipated to consist of the following major elements:
  Construction of 0.72 mile long roadway pavement
  Two roundabouts at the southern and northern termini
  Two bridges crossing Reddy Branch stream and Meadow Branch stream
  SWM and ESC
  Retaining walls
  Removal of a bridge
  Replacement of the culvert at Brookeville Road
  Traffic barrier
  Landscaping
  Signing and pavement marking
  Stream relocation, wetland mitigation, forest mitigation.

## Slide 10: Project Challenges:
  Watercourse 1 (Reddy Branch) and Watercourse 2 (Meadow Branch) are Class IV-P waters (Recreational Trout Waters and Public Water Supply). Structures are proposed to cross these two streams.
  Intermittent Watercourse 3 and Perennial Watercourse 4 are tributaries to Meadow Branch. Watercourse 3 is expected be impacted and would require mitigation. Impacts to Watercourse 4 needs to be avoided.
  In-stream work is not permitted from March 1 through May 31.
The alignment goes through M-NCPPC parkland and ESD facilities for SWM were not considered in original study. Avoidance and minimization of additional of increased impacts to parkland and forest is desired.
Archeological sites are expected to be impacted and the impacts should be minimized.
Avoidance and minimization of temporary impacts to natural resources during construction is desired.

## Slide 11: Major Stakeholders
Montgomery County
Maryland-National Capital Park and Planning Commission
Town of Brookeville
Maryland Department of the Environment
Maryland Department of Natural Resources
US Army Corps of Engineers
US Fish & Wildlife Service
US Environmental Protection Agency

## Slide 12: Construction Management at Risk (CMAR) Project Delivery

## Slide 13: What is CMAR?
A project delivery method where SHA utilizes a two-phase construction contract with a General Contractor to:
  Provide Preconstruction Services which may include, but are not limited to, constructability analysis, value analysis, scheduling, site assessments, and cost estimating;
  Construct the project based on final design plans (or design packages) at an agreed Guaranteed Maximum Price (GMP)

## Slide 14: Authority
State – Code of Maryland Regulations (COMAR) 21.05.10
Federal – Moving Ahead for Progress in the 21st Century (MAP-21) – Construction Manager/General Contractor (CM/GC)

## Slide 15: Project Delivery Methods
Design-Bid-Build
CMAR
Design-Build

## Slide 16: Project Development
Design-Bid-Build
(DBB)
CMAR
Design-Build
(DB)
Preliminary Design
Detailed/Final Design
Bid
Construction
Preliminary Design
Detailed/Final Design
Construction
Design-Build
Procurement
Preliminary Design
Detailed/Final Design
Construction
CMAR
Procurement

## Slide 17: Reasons for choosing CMAR
Shorten Project Delivery
Project Complexity
Contractor Input During Design
High Number of Potential Risks/Risk Allocation
Scope Flexibility/Maximizing Dollars
Cost Analysis of Multiple Design Options
Informed Owner Decision Making

## Slide 18: CMAR – Risk Allocation
Chart: 
| DBB | DB | CM/GC
Owner | 15 | 5 | 10
Contractor | 5 | 15 | 10
DBB DB CMAR

## Slide 19: CMAR Expectations
Meet Project Goals
Fair Market Price
  At or Below Proposed Price
Improved Schedule
Fewer Change Orders

## Slide 20: CMAR Benefits
Opportunity to bring on contractor during the design phase to work as an integrated team with the owner and its consultant/engineer to deliver the most efficient, and cost effective design
Promotes innovation & collaboration
Owner maintains decision making authority
Greater cost certainty through GMP and reduction in change orders
Still allows phased construction similar to design-build resulting in accelerated completion times. Phases must be severable.
Risk identification & management during design phase and controlled by the team
Owner gets up front benefit of value engineering
CMAR design documents are biddable packages, not necessarily full set of biddable contract documents

## Slide 21: CMAR Potential Risks
Transparency – Technical Qualifications and Approach are Main Elements for Selection
Cost Validation – “Negotiated” vs. Bid
Culture – New Process for All (SHA, Consultants, Contractor, Regulatory Agencies, Etc.)
Risk – Limited Historical Usage for Heavy Highway Construction

## Slide 22: Procurement of General Contractor
Best Value Selection
One Step Process
Technical Ratings - Adjectival
Method of Selection – Best Value
  Technical Proposal – Qualifications/Past Performance & Project Approach
  Price Proposal – Preconstruction Fee/Other Elements
Technical Proposal is significantly more important than Price

## Slide 23: CMAR Project Team
Owner (SHA)
Engineer under separate Contract with owner to provide all design services for the project.
Two Phase Contract with General Contractor (GC)
    Phase 1 – Preconstruction Services - GC considered part of the design team providing constructability, cost, schedule and risk management input.
    Phase 2 – GC and Owner agree on GMP to construct the project based upon final design plans (or design packages). If GMP cannot be agreed upon, then advertise as design-bid-build.

## Slide 24: Independent Cost Estimator
Independent party hired by SHA to prepare a series of detailed estimates.
Estimates are performed independently from Contractor and SHA’s Designer.
Estimates are utilized as a basis of comparison for review of Contractor’s GMPs and award of Construction Contract.

## Slide 25: Cost Model Development
Develop Cost Model for Project
  Opinion of Probable Construction Cost (OPCC)
  Guaranteed Maximum Price (GMP)
Elements of Cost Model
  Profit and Indirect Overhead Percentage
  Equipment Types and Rates
  Material Sources
  Subcontractor Items of Work
  Risk Agreement and Assignment
  Schedule

## Slide 26: Cost Model Development
OPCC
  To be submitted at various Design Completion milestones
  Blind Estimate Comparison
  Report of Items Outside of Tolerance (>10%)
  Reconciliation Meeting to discuss differences in bidding assumptions

## Slide 27: Once Design is Complete
Contract documents have been developed collaboratively by team
Follow typical procedures
  DBE goals established for construction
  2008 Standard Specifications and current SP/SPIs
GMP - Contractor and ICE will independently price project

## Slide 28: Once GMP is Submitted
Contractor and ICE prices
Price Reconciliation Meetings as needed
Up to 3 GMP Submittals allowed
  Accept GMP and Award Contract
  Terminate Contract and Bid Project as DBB

## Slide 29
Sean Campion P.E.
Assistant Chief, Innovative Contracting Division
Maryland State Highway Administration
scampion@sha.state.md.us
(410) 545-8863
Questions/Feedback?