## Slide 1: The Successes and Challenges of Delivering a P3 – The Purple Line – Maryland’s New Light Rail System
March 10, 2020

## Slide 2: PRESENTER
Kevin Oberheim, PE, CCM
PMC Construction Manager
Maryland Transit Administration/Program Management Consultant
Project Manager, RK&K

## Slide 3: WHAT IS THE PURPLE LINE?
Bethesda, MD
New Carrollton, MD
16.2 Miles
(Measured along Alignment)

## Slide 4: THE GREAT CONNECTOR
The Purple Line will connect:
  4 Metrorail Stations
  All 3 MARC Lines
  Amtrak’s NE Corridor
  Multiple local and regional bus services
  Region’s largest transit centers
  MD’s flagship university – 5 stations
    Adelphi Road UMGC – UMD
    Campus Drive – UMD
    Balt. Ave. College Park – UMD
    College Park Metro – UMD
    Riverdale Park North – UMD

## Slide 5: PROJECT SCALE
32
26
18
>250
Miles of Track
Miles of Drainage Construction
Miles of Water/Sewer/ Gas Utility Relocations
Walls
>10
Miles of New Bike Lanes & Trails
Bridges
33

## Slide 6: KEY PROJECT PARTICIPANTS
Key Stakeholders Include:
MDOT SHA
University of Maryland
Montgomery County
Prince George’s County
WMATA
CSXT
Utility Companies (17+)

## Slide 7: PROJECT PURPOSE AND NEED
Relief for Bus Services
Reliable & Rapid East-West Transit
Access to Metro System
Changing Land Uses & Job Growth

## Slide 8: LIGHT RAIL SYSTEM

## Slide 9: PROJECT CHARACTERISTICS
Headways
  Peak: 7 ½ minutes
  Off-Peak: 10-15 minutes
Service
  Similar to Metrorail hours
  ≈ 30% of riders to use Metro
  Just over an hour
  Short trips vs end to end ridership
Daily Riders
  Year 2030  69,000
  Year 2040  74,000

## Slide 10
PUBLIC PRIVATE PARTNERSHIP (P3) AGREEMENT – DELIVERY MODEL

## Slide 11: CONTEXT – SOME OF THE CHALLENGES
MTA already operates rail lines, but…
  MTA’s first rail service in the Washington region
    More than 30 miles from core service area of Baltimore
  Largest project in MTA history
  MTA hasn’t constructed a new rail line in more than 20 years
    Rail construction, integration, and startup is challenging
Dense corridor with 800+ utility relocations, 600+ property acquisitions
Extensive third-party coordination required
  MOAs with 17 utility companies, 2 counties, WMATA, UMD-College Park, CSX
Sophisticated stakeholders and communities with high expectations

## Slide 12: MDOT MTA’S PURPLE LINE DELIVERY APPROACH: DBFOM P3
Combines the design, construction, financing, operations and maintenance into one umbrella contract with a “concessionaire”
  6 year design & construction + 30 year O&M period
  Shares risk between MTA and the Concessionaire
  Based on performance standards, not detailed specifications
  “Pay for performance” – Payments linked to availability & outcomes
  30-year handback provisions protect long-term public interest
Status: P3 contract awarded 2016; Construction began summer 2017, approximately 25% complete to date
First Light Rail Vehicles (LRV) being tested at CAF facility in Elmira, NY

## Slide 13: OVERVIEW OF PURPLE LINE P3 STRUCTURE
Approach: Design-Build-Finance-Operate-Maintain (DBFOM) Public-Private Partnership (P3) Concession with Availability Payments (APs)
  30-Year Period
  Concessionaire responsible for operations, maintenance, and capital renewal/replacement; asset handback requirements at end of P3 term
  MTA (“Owner”) responsible for fare policy, specification of minimum amount of service, ridership & fare revenue risk, electricity costs, and policing
  6 Years
  Concessionaire responsible for final design, construction of Purple Line and some 3rd party improvements and financing the project (in part using public funding contributions)
  MTA (“Owner”) responsible for right-of- way acquisition, public outreach and quality assurance oversight
Design & Construction
O&M and Capital Renewal

## Slide 14: CONTRACTING STRUCTURE
O&M Contract
Design-Build Contract
The Company and Equity Investors
(Meridiam Infrastructure Purple Line, LLC) 70%
(Fluor Enterprises, Inc.) 15%
(Star America Purple Line, LLC) 15%
Contracting Authority
P3 Agreement and Performance Specifications
Interface Agreement
(Fluor Enterprises, Inc.) 50%
(The Lane Construction Corporation)
30%
(Traylor Bros., Inc.)
20%
O&M Contractor
(Fluor Enterprises, Inc.) 40%
(Alternate Concepts, Inc.)
40%
Design-Build Contractor
(CAF USA, Inc.)
20%
Lenders
PLTP PAB Holders
TIFIA
Loans

## Slide 15
REAL ESTATE ACQUISITIONS

## Slide 16: PURPLE LINE CORRIDOR
Developed urban/suburban corridor
Mix of residential and commercial areas
Purple Line would generally operate on or adjacent to existing streets
West segment former B&O railroad corridor

## Slide 17: PROPERTY ACQUISITION CHALLENGES
Large Number of Acquisitions
Long Term Construction
Acquisitions at 30% Design
Project Schedule and MTA Risk
Lack of Quick-Take Condemnation
Railroad Property Acquisition
Team Organization
MD 384/Colesville Road
View of CSX railroad bridge
16th Street Shopping Center

## Slide 18: PURPLE LINE ACQUISITIONS
Over 600 properties impacted by the Purple Line requiring acquisitions totaling approximately 86 acres.
Partial Acquisitions: 82%
Full Acquisitions: 18%
85% of Purple Line acquisitions located adjacent to State-owned Right of Way
Total Acquisitions include:
  Gas Stations
  Apartment Units
  Strip Retail Centers
  Office Properties
  Single Family Dwellings
Business Acquisitions at Brookville Road

## Slide 19: UTILITY RELOCATIONS

## Slide 20
CONSTRUCTION & PROJECT HIGHLIGHTS

## Slide 21: PROJECT STATUS UPDATE
Construction is underway throughout the 16.2 mile corridor
Approximately 15 of 16 miles are under construction
  Design: 95% complete
  Construction: 25% complete
Right-of-way acquisitions are complete
Utility relocations underway along entire alignment
LRV Update:
  68 carshells (13 carsets, working on 14th) complete
  33 carshells have been painted
  LRV #1 and #2 are undergoing static and dynamic testing in Elmira, NY
Community Outreach – key element of the project
Art-in-Transit

## Slide 22: LIGHT RAIL VEHICLE (LRV)
Quiet and modern, vehicles are 5 modules each spanning a total of 140 feet long (longest in the USA)
80 seats are provided
80% low floor and wide doorways specifically designed to meet ADA requirements
Eight wheelchairs and eight bicycles can be accommodated on board simultaneously
Comfortable, well-lit interiors

## Slide 23: CONSTRUCTION HIGHLIGHT – BETHESDA
The Bethesda Shaft (elevator) & Bethesda Purple Line Station:
Connects two transit systems – Purple Line and
WMATA’s Red Line
Adds (6) high speed elevators for Red Line
Connects to the new mixed use tower currently
under construction
Construction Challenges:
  Depth of shaft is currently greater than 100 feet
  (31m), concrete lining is being placed
  Complex Support of Excavation (SOE) System due to existing geotechnical conditions and WMATA requirements
  – strut and waler system
  Multi-lift concrete liner
  Complex work zone – WMATA, Purple Line, & Carr Properties all sharing the same work zone

## Slide 24: CONSTRUCTION HIGHLIGHT – BETHESDA SOE
Hydraulic SOE System
  Addressed pressure transfer between vertical beams
  Supports are quickly installable and reusable
  Ease of use adds, mitigates many issues often encountered with the large, steel beam systems traditionally used in such situations
Construction Work to be Undertaken
  Excavation of cavern in bedrock
  Widening the shaft footprint
  Mined cavern to the WMATA station
The cavern excavation will use classical drill-and-blast excavation and shotcrete support
Work is adjacent to WMATA Red Line, close coordination with WMATA during blasting to minimize disruption to Red Line service

## Slide 25: CONSTRUCTION HIGHLIGHT – LYTTONSVILLE
June 4, 2019 the Talbot Ave. Bridge was deconstructed to make way for a modern and wider bridge with sidewalks. The Purple Line will pass under the new Talbot Ave. Bridge next to the CSX tracks. Pile driving for the new bridge abutments was completed in December of 2019. The new Talbot Bridge is scheduled to be open by the end of 2020.

## Slide 26: CONSTRUCTION HIGHLIGHT – SILVER SPRING
Extensive coordination with Montgomery County, WMATA, CSX, and other agencies has been ongoing to set the first girders for the LRV bridge over WMATA and CSX tracks in Silver Spring in January of 2020. Additionally the Capital Crescent Trail (CCT) trestle was set over Colesville Rd. in January of 2020.
LRV Girders over WMATA’s Metro Red Line
CCT trestle being erected

## Slide 27: CONSTRUCTION HIGHLIGHT – LONG BRANCH
Plymouth Tunnel:
Length - 1,100 ft. (335m) under a suburban neighborhood
Tunnel excavation completed in March of 2019
PVC sheet waterproofing membrane and final lining installed
Shotcrete liner in lieu of form-and-pour
Geotechnical conditions - soft ground in the top heading and relatively hard rock in the bench and invert
Extensive noise and vibration monitoring during construction

## Slide 28: CONSTRUCTION HIGHLIGHT – LONG BRANCH
Plymouth Tunnel:
Sequential Excavation Method (SEM) tunneling method used due to mixed face conditions
Economical for relatively short tunnels
Groundwater control required throughout construction to maintain the heading
Portal of the mined section is supported by a secant pile wall

## Slide 29: CONSTRUCTION HIGHLIGHT – LONG BRANCH
Manchester Place Station
West of the Plymouth Tunnel
Continues in the open cut section
SOE is comprised of soldier piles and lagging and a secant pile wall at the tunnel portal
Station structure is cast-in-place concrete

## Slide 30: CONSTRUCTION HIGHLIGHT – UNIVERSITY BLVD.
Work on University Blvd. continues to progress with the removal of medians and utility relocations to make way for the Purple Line tracks that will be in the center of the road alongside vehicular traffic.

## Slide 31: CONSTRUCTION HIGHLIGHT – COLLEGE PARK
Work is underway on the Purple Line College Park Metro Station on River Rd. Pictured is site work and the removal of the asphalt bus loop.

## Slide 32: CONSTRUCTION HIGHLIGHT – RIVERDALE PARK
Riverdale Rd. bridge piers have been constructed that will support the Riverdale Park-Kenilworth aerial station. The first girders are scheduled for erection late February of 2020.

## Slide 33: CONSTRUCTION HIGHLIGHT – GLENRIDGE
Steel framing of the Glenridge Operations and Maintenance Facility (OMF) was completed in July of 2019. This facility will maintain and clean the Light Rail Vehicles (LRVs) as well as house the Purple Line administration and operational staff. First LRV scheduled to arrive October 2020.

## Slide 34: CONSTRUCTION HIGHLIGHT – NEW CARROLLTON
The first section of rail for the Purple Line was installed on Ellin Rd. in September of 2019. This is embedded track where the Purple Line will run on Ellin Rd. with vehicular traffic.

## Slide 35: ART-IN-TRANSIT PROGRAM
The mission of the Purple Line Art-In-Transit program is to make public art an integral element of the project
Art will be incorporated into stations to enrich the aesthetics of the light rail system and support neighborhood identities
Artists have been selected, art proposals have been refined based on input received, and contracts are being negotiated
$6M for artwork at 21 stations, allocated equally among 2 counties
Station artwork to be installed between 2020 – 2021

## Slide 36: ADJACENT DEVELOPMENT AND CHALLENGES
Adjacent Development
  At least 36 development projects planned or underway along the alignment
  Contractor coordination with adjacent contractors
  Shared Work Sites
Regional Construction
  I-66 Widening - $3.7 Billion
  I-395 - $0.5 Billion
  Silver Line Phase II - $2.7 Billion
  DC Water Boundary Tunnel - $0.5 Billion
  DDOT South Cap Bridge $0.4 Billion
  WMATA Station Rehabilitation - $1.5 Billion
Gilbane – Planned Development in Prince George’s County
Carr Properties – Planned Development Montgomery County

## Slide 37: WHAT ABOUT CONCRETE?
Uses Throughout the Project
  Bridge substructures and superstructures
  10 bridges with concrete girders (11,000+ LF)
  70,000+ LF of embedded or direct fixation track
  Shotcrete
  500,000+ SF Precast MSE Wall Panels
To Date
  55,000 CY delivered
  7500 test cylinders cast
  2100 field tests performed
Glenridge OMF – Slab-On-Grade Shop Floor
Silver Spring LRT Aerial – Pier 3 Cap Placement

## Slide 38: WHAT ABOUT SHOTCRETE?
Plymouth Tunnel
  11,500+ CY silica fume shotcrete produced on site
  NRMCA Certified Batch Plant
  Used for both primary and secondary liners
  Fireproofing polymer fibers used in secondary liner
  Special regulating layer (modified gradation) for smoothness
Other Uses
  Rock Creek Slope Stabilization
  Soil Nail Walls
Plymouth Tunnel Final Shotcrete Liner
On-Site NRMCA Certified Batch Plant

## Slide 39
QUESTIONS?

## Slide 40: CONTACT US
Kevin Oberheim, PE, CCM PMC Construction Manager| kevin.oberheim@purplelinemd.com
Tel: +1 410.241.1120
@PurpleLineMD
/MarylandPurpleLine
Follow us on Social Media
Visit our website: www.purplelinemd.com